WIOA Alignment Group Planning: 
2024-2028 Combined WIOA State Plan

Preparation/Submission Timeline

Fall 2023: Federal partners release 2024 Plan guidance (Date TBD)

Key Dates

- End of September - Strategic Planning concludes

- October 31 - First Draft completed

- November 27 - Second Draft completed

- December 8 - Draft submitted for public comment

- January 18 - Draft submitted to Core Partners for approvals

- January 31 - Approvals Due

- February 1 - Draft submitted to Governor’s Office for approval

- February 28 - Plan officially submitted via portal

| MONTH | ACTIVITY |
| --- | --- |
| July | 7/31 - WIOA Alignment Group initial planning discussion on WIOA 2024-2028 state plan process and timeline. Goal is to solicit feedback and approve the timeline. |
| August | 8/1 - 8/28 - 1 on 1 Operational and Planning meetings with WIOA Alignment Partners |
|  | 8/28 - WIOA Alignment Group Meeting discussing strategic planning, new norms for the group, and evaluation of current goals. |
| September | 9/6 - September Governor’s Workforce Development Board (GWDB) meeting |
|  | 9/25 - WIOA Alignment Group meeting, finalizing State Plan writing process and areas of focus. |
|  | 9/29 - Assigned sections distributed to WIOA Core Partners |
| October | 10/2 - 10/31 - WIOA Core Partners edit individual State Plan sections |
|  | 1st Draft of State Plan sections Due October 31s |
|  | 10/30 - WIOA Alignment Group meets. Discuss progress on sections, questions/concerns, etc. |
| November | 11/1- 11/10 - Policy Unit reviews sections |
|  | 11/13 - 11/27 - Policy Unit provides feedback and works with partners to revise sections |
|  | 11/29 - WIOA Alignment Group meets (meeting moved to Wednesday). Policy Unit provides update on progress |
|  | 11/28 - 12/5 - DWDAL Policy Unit compiles/edits full State Plan and prepares “Crosswalk” for GWDB: - New Prompts, - Significant Modifications, and - Emphasized topics. Submit crosswalk to GWDB for inclusion on agenda during 12/6 meeting. |
| December | 12/6 - GWDB Meeting. DWDAL presents Crosswalk and requests approval to submit for public comment. Also DWDAL suggests Board to review State Plan during upcoming public comment period |
|  | 12/8 - 1/5 - State Plan released for public comment |
| January | 1/8 - 1/12 - Policy team reviews and compiles public comments |
|  | 1/15 - Early WIOA Alignment Group meeting scheduled to review public comments |
|  | 1/8 - 1/17 - DWDAL Policy Unit compiles FINAL DRAFT State Plan and prepares 2022 State Plan Summary for GWDB/Governor’s Office: - Responses to new prompts, - Brief section-by-section updates, and - Trends/themes. |
|  | 1/18 - DWDAL shares FINAL Draft and 2022 State Plan Summary via email with partners who want to review entire State Plan for approval: - GWDB - MD Labor - DHS - MSDE DORS |
|  | 1/31 - Approval due from core partner leadership |
| February | 2/1 - 2/23 - Governor's Office reviews and approves |
|  | 2/1 - 2/28 - Policy Unit uploads State Plan into portal |
| March | 3/1 - State Plan due |
| April- June | Work with federal partners on revisions |
| July | Full Federal Approval - Governor announces approved Plan - Plan published online |

Partner Logistics

|  | Point of Contact |
| --- | --- |
| MD Labor (Overall) | Robert Ruffins/Dylan McDonough |
| MD Labor Title I/III | Lloyd Day |
| MD Labor Title II | Perketer Tucker |
| MD Labor UI | Likivu Speaks |
| GWDB | Michael DiGiacomo |
| DHS-TANF | Tina Turner |
| DHS- SNAP E&T | Mischelle Williams and Candice Roberts |
| DORS | Patrick Peto |
| DHCD | Angela Fraser |